## Sheet1
PROGRESS CHART
Userstories | User stories
|  | Actual hours (cumulative) | 144 | 336 | 536 | 712 | 872 | 1032 | 1176 | 1280 | 1384 | 1512 | 1624 | 1768 | 1888 | 1968 | 2144 | 2208 | 2304 | 2464 | 2552 | 2640 | 2720 | 2800 | 2816 | 2912 | 3072 | 3208 | 3280
|  | Actual hours per sprint | 144 | 192 | 200 | 176 | 160 | 160 | 144 | 104 | 104 | 128 | 112 | 144 | 120 | 80 | 176 | 64 | 96 | 160 | 88 | 88 | 80 | 80 | 16 | 96 | 160 | 136 | 72
(2 months )
|  |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Sprint 17 | Sprint 18 | Sprint 19 | Sprint 20 | Sprint 21 | Sprint 22 | Sprint 23 | Sprint 24 | Sprint 25 | Sprint 26 | Sprint 27
Reading in JSON configuration files (Create configuration module) | Create configuration module |  | 6
Reading in standardized spatially and temporally distributed climate input data (Create data handling module) | Create climate forcing and static data handling module |  | 1
Run the calibrated WaterGAP with different climate change scenarios as input | Update configuration module to run different climate change scenarios as input |  | 1
Implementation of a new PET algorithm (Flexible algorithm) | Implement PET algorithm |  | 136 | 40
Implement net radiation | Implement net radiation algorithm |  |  | 1
Implement canopy storage and fluxes | Implement canopy algorithm |  |  | 20
Implement snow storage and fluxes | Implement snow algorithm |  |  | 131 |  | 72 | 24
Implement soil storage and fluxes | Implement soil algorithm |  |  |  | 200
Write unit test for ReWaterGAP (vertical water balance functions and lateral waterbalance**) | Unit testing |  |  |  |  | 72
Check code and correct errors (bugs, code format, variable names, units) | Code quality check ( (bugs, code format, variable names, units) |  |  |  |  | 32
Implement response form code reviews | Peer code review | [5 empty] | 8
Read through ISIMIP quality control tool as a benchmark for the spatial testing tool | Read through ISIMIP quality control tool as a benchmark for the spatial testing tool | [5 empty] | 96
Improve parallelization scheme (on snow module) by allowing user to select chunk size | Improve runtime of snow module algorithm | [5 empty] | 24
Saving NETCDF outputs in chunks for very large runs (eg. 100 years) | NetCDF output chunking for large runs | [5 empty] | 8
Implement ground water storage and fluxes | Implement groundwater algorithm | [6 empty] | 160
Implement local lakes and wetlands water storage and fluxes | Implement local lakes and wetlands algorithm | [7 empty] | 144 | 104
Implement global lakes and wetlands and river water balance including storage and fluxes | Implement global lakes and wetlands and river algorithm | [9 empty] | 104 | 128 | 96
Restart from any daily snapshot or prescribed state | Develop a daily snapshot restart feature | [11 empty] | 16
ReWaterGAP and ISIMIP QA tool integration (hackfest) | ReWaterGAP-ISIMIP QA tool integration | [12 empty] | 24
Actual and potential net abstractions from surface water and groundwater | Implement surface and ground water abstraction algorithm | [12 empty] | 120 | 120 | 80 | 176 | 64 | 96 | 160
Optimize runtime of WaterGAP | Improve ReWaterGAP runtime | [19 empty] | 88
Neighbouring cell water supply algorithm assessment (Wateruse Balance ) & Runtime analysis | Water use balance assessment | [20 empty] | 88 | 16 | 8 | 8
Water Balance | Global water balance assesement | [22 empty] | 72 | 8
Calibration scheme | Implement Calibration scheme | [21 empty] | 64 |  |  | 96 | 160 | 136 | 72
|  | Sprint | No. of user stories completed | No. of user stories planned | Total working hours | no. of working days | sprint | Remaining user stories | Remaining working hours | [5 empty] | vertical | 872
|  | 1 | 3 | 4 | 144 | 18 | 0 | 24 | 3280 | [5 empty] | lateral | 1800 | netabs | 816
|  | 2 | 3 | 4 | 192 | 24 | 1 | 21 | 3136 | [5 empty] | calibration | 608
|  | 3 | 1 | 1 | 200 | 25 | 2 | 18 | 2944 | [6 empty] | 3280
|  | 4 | 2 | 3 | 176 | 22 | 3 | 17 | 2744
|  | 5 | 5 | 5 | 160 | 20 | 4 | 15 | 2568
|  | 6 | 1 | 1 | 160 | 20 | 5 | 10 | 2408
|  | 7 | 0 | 1 | 144 | 18 | 6 | 9 | 2248
|  | 8 | 1 | 1 | 104 | 13 | 7 | 9 | 2104
|  | 9 | 0 | 1 | 104 | 13 | 8 | 8 | 2000
|  | 10 | 0 | 1 | 128 | 16 | 9 | 8 | 1896
|  | 11 | 2 | 2 | 112 | 14 | 10 | 8 | 1768
|  | 12 | 1 | 2 | 144 | 18 | 11 | 6 | 1656
|  | 13 | 0 | 1 | 120 | 15 | 12 | 5 | 1512
|  | 14 | 0 | 1 | 80 | 10 | 13 | 5 | 1392
|  | 15 | 0 | 1 | 176 | 22 | 14 | 5 | 1312
|  | 16 | 0 | 1 | 64 | 8 | 15 | 5 | 1136
|  | 17 | 0 | 1 | 96 | 12 | 16 | 5 | 1072
|  | 18 | 1 | 1 | 160 | 20 | 17 | 5 | 976
|  | 19 | 1 | 1 | 88 | 11 | 18 | 4 | 816
|  | 20 | 0 | 1 | 88 | 11 | 19 | 3 | 728
|  | 21 | 0 | 2 | 80 | 10 | 20 | 3 | 640
|  | 22 | 0 | 2 | 80 | 10 | 21 | 3 | 560
|  | 23 | 2 | 2 | 16 | 2 | 22 | 3 | 480
|  | 24 | 0 | 1 | 96 | 12 | 23 | 1 | 464
|  | 25 | 0 | 1 | 160 | 20 | 24 | 1 | 368
|  | 26 | 0 | 1 | 136 | 17 | 25 | 1 | 208
|  | 27 | 1 | 1 | 72 | 9 | 26 | 1 | 72
[7 empty] | 27 | 0 | 0